PROCESS MAPS & GAP ANALYSIS

ServiceOntario Digital Transformation Initiative

Prepared by:  Aishwarya Senthil — Business Analyst

Version:  1.0

Date:  June 2026

Phase:  3 of 5 — Process Mapping & Gap Analysis

Builds on:  Phase 1 (Charter) · Phase 2 (Stakeholder Analysis)

BA Portfolio Project  ·  Phase 3 of 5

1. What is Process Mapping?

Process mapping is a BA technique for visualising how work actually flows through an organisation — who does what, in what order, and where things go wrong. A BA creates two versions: the As-Is map (current state, warts and all) and the To-Be map (the optimised future state). The gap between them becomes the project's work.

The As-Is map is built from interviews with front-line staff and subject matter experts — the people who live the process every day. The To-Be map is built collaboratively with stakeholders based on business objectives defined in the Project Charter (Phase 1).

| BA NOTE | Process mapping is one of the most interview-tested BA skills. If someone asks 'walk me through how you approach process improvement,' this is your answer. As-Is → pain points → To-Be → gap → requirements. That flow is the BA's core methodology. |
| --- | --- |

2. As-Is Process Map — Current State

The following map shows how a health card or driver's licence renewal currently flows through ServiceOntario. Each step is followed by the pain point it creates. These pain points were identified through simulated stakeholder interviews with front-line staff (Phase 2).

Current State: Health Card / Licence Renewal

| Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Submit Paper Form Branch or mail only | Manual Data Entry Ops re-keys all fields | Document Check Manual completeness review | Credit Bureau Pull Analyst pulls manually | Risk Scoring Spreadsheet model | Manager Sign-off Paper approval required | Decision Letter Mailed to applicant |
| ⚠ No digital channel | ⚠ 12% error rate | ⚠ 40% returned incomplete | ⚠ Slow, inconsistent | ⚠ Varies by analyst | ⚠ Adds 2–3 days | ⚠ Takes 3–5 days by post |

Key observations from the As-Is process:

- The entire process is paper and in-person dependent — there is no digital entry point for residents

- Manual data re-entry by operations staff introduces an estimated 12% error rate, causing downstream delays

- 40% of applications are returned to the resident due to missing documents — adding 5–7 business days per resubmission loop

- Risk scoring varies by analyst — the same application may receive different outcomes depending on who processes it

- The decision is communicated by post, adding 3–5 days after an already lengthy process

- Total average cycle time: 18–22 business days from submission to decision

| BA NOTE | In a real engagement, this section would be validated with front-line staff before presenting to leadership. You never present an As-Is map without confirming it reflects reality — otherwise you lose credibility with the people who live the process. |
| --- | --- |

3. To-Be Process Map — Future State

The To-Be map shows the redesigned process after digital transformation. It directly addresses each pain point identified in the As-Is map. Seventy percent of eligible applications will be fully auto-decisioned with no human involvement required.

Future State: Health Card / Licence Renewal (Digital)

| Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Digital Portal Web + mobile, 24/7 | Auto Doc Check OCR + rules engine | Live Bureau API Automated credit pull | ML Scoring Engine Standardised model | Auto Decision Rules threshold | Digital Workflow Exception review queue | Instant Notification App, email, SMS |

Key improvements in the To-Be process:

- Digital portal replaces paper — residents apply online 24/7 from any device, in English or French

- Automated document check with real-time checklist eliminates the 40% resubmission loop

- Live bureau API replaces manual credit pull — faster, consistent, auditable

- Standardised ML scoring engine eliminates analyst inconsistency — compliance-ready

- 70% of applications auto-decisioned in under 2 hours — no human touchpoint needed

- Remaining 30% routed to analyst queue with a 2 business day SLA

- Decision delivered instantly via app, email, and SMS — no postal wait

- Target cycle time: 3–5 business days (down from 18–22)

| BA NOTE | The To-Be map should always trace back directly to the business objectives in the Project Charter. Every improvement here links to a KPI defined in Phase 1. That traceability — from problem to objective to process change — is what makes a BA's work defensible. |
| --- | --- |

4. Gap Analysis

The gap analysis documents every specific change required to move from the As-Is state to the To-Be state. Each gap is prioritised using MoSCoW: Must Have (project fails without it), Should Have (important but not critical for launch), Could Have (nice to have), Won't Have (explicitly excluded).

| Pain Point (As-Is) | Future State (To-Be) | Impact | Priority | Owner |
| --- | --- | --- | --- | --- |
| Paper-only application — branch or mail | Digital portal: web + mobile, 24/7 access | High | Must Have | Ontario Digital Service |
| Manual data re-entry by ops staff | API-based digital intake — no re-keying | High | Must Have | IT / ODS |
| 40% of applications returned incomplete | Real-time document checklist + instant alert | High | Must Have | ServiceOntario Ops |
| Manual credit bureau pull (per analyst) | Automated live bureau API integration | High | Must Have | IT / Credit Systems |
| Inconsistent scoring across analysts | Standardised ML/rules-based scoring engine | Medium | Should Have | Risk & Compliance |
| Paper manager sign-off required | Digital approval workflow with audit trail | Medium | Should Have | ServiceOntario Ops |
| Decision communicated by post (3–5 days) | Instant decision via app, email, and SMS | Medium | Should Have | IT / Comms |
| No French-language digital option | Bilingual portal (EN/FR) from day one | High | Must Have | ODS / Legal |
| No accessibility-compliant digital channel | AODA-compliant interface with screen reader support | High | Must Have | AODA Advisor |

| BA NOTE | MoSCoW prioritisation is a standard BA tool. When a developer or project manager asks 'what do we build first?' this table is your answer. It also protects you in scope disputes — if something isn't in this table, it needs a change request. |
| --- | --- |

5. Summary of Findings

| Metric | As-Is (Current) | To-Be (Target) | Improvement |
| --- | --- | --- | --- |
| Average cycle time | 18–22 business days | 3–5 business days | ~80% reduction |
| Digital channel availability | None | Web + mobile, 24/7 | New capability |
| Auto-decisioned applications | 0% | 70% | New capability |
| Document resubmission rate | 40% | <5% (real-time checklist) | ~88% reduction |
| Cost per transaction | $28.40 | <$8.50 | ~70% reduction |
| Resident satisfaction | 54% | Target: 80%+ | +26 points |
| Scoring consistency | Variable by analyst | Standardised model | Compliance ready |

| BA NOTE | This summary table is what you show executives. They don't need to read the process maps — they need the before/after numbers. A BA always translates detailed findings into a clear, quantified summary for leadership audiences. |
| --- | --- |

ServiceOntario Digital Transformation  ·  Process Maps & Gap Analysis v1.0  ·  BA Portfolio Project — Phase 3 of 5